## HelpPage
| #VALUE! | See our terms and conditions, click here.
The project planner offers a comprehensive set of features, including automatic date calculation based on various factors like weekends and holidays, a dynamic Gantt chart that updates in real-time, a detailed project summary with drill-down capabilities, and robust budget planning tools to track costs against set budgets.
| Project Planner | Citations:
1 | Project Summary | Overall project summary report. Highlight bymonth , overall time-line progress chart and % donet and budget. | ProjectSummary
2 | Report | A report that shows tasks that are completed >90%. Displays all information for the task including budget. | Report
3 | Project Schedule | Gantt chart for visualising timelines and tracking task progress over time. | ProjectSchedule
4 | Project Plan | This is where you specify tasks, resources, timelines, dependencies, and other project details. | ProjectPlan
5 | Bank Holidays | This is where your add you own bank holidays to adjust task durations. | Holidays
6 | Staff Holidays | This is where you add staff holidays, dates to adjust task durations and other information related to dates. | Holidays
7 | Staff Listing | Specify a list of staff resources used in the project and budgets for their rates. | Staff
8 | Project Information | Set the Story/Project short code, Project Title, and Project Start Date, which are used on various pages. | Information
9 | Date Generator | A tool to help generate a list of weekday dates with type and staff for easy copy to staff holiday table. | Holidays
Key Features
1 | Automatic Date Calculation | Project Plan dates are updated based on weekends, bank holidays, staff holidays, task dependencies, task effort, and previous task assignments.
2 | Dynamic Gantt Chart | The Gantt chart automatically updates based on the Project Plan. Note that the user must specify a Task Name, Effort, and ensure the percentage completed is not set to "N/A" (i.e., 0% or above) to display the task.
3 | Project Summary and Drill Down | The Project Summary feature allows users to drill down into specific months, highlighting start dates, end dates, and the count of different task statuses. End dates take priority over start dates and are used to calculate the number of statuses in the month.
4 | Budget Planning | The project planner provides a comprehensive overview of the budget versus actual costs.
Notes
1 | Dates | Dates must be in UK format. Other formats are not currently supported (requires testing).
2 | Applying Holidays | Bank holidays are applied to all staff, whereas staff holidays are only applied to the individual staff member based on the start date and end date for a task. Accurate Date Calculation: Each dependency must be specified for the Automatic Date Calculation to accurately determine start and end dates. Staff Holiday Reflection: Staff holidays are reflected in the holiday count field. This table can be used to capture additional delays to a project for a given assignee, capturing a reason and notes. This information is useful when carrying out a project review/retrospective. Holiday Impact on Task Start Dates: If a holiday date coincides with a task's start date, the system automatically shifts the start date to the next available working day. Please note: This automatic shift is not reflected in the holiday count field. Only holidays occurring after a task’s start date are included in the count. You can use the holiday calendar to view the holidays for a given task or by a role.
3 | Ref Number | In the Project Plan, at least one reference number must exist, starting with "1.1.0" and following this format. Each task must have a unique reference number. If a task is not required, do not enter a reference number, as it is used in date calculation logic and will result in an incorrect project plan.
4 | Information | Reference data values must be unique, and at least one entry must exist for each table (Bank Holidays, Staff Holidays, and Staff).
5 | Filters | Filters can be used to tidy up views, but remember to re-apply filters after making changes.
6 | Macros | This spreadsheet does not contain any Macros or VBA code.
7 | Budgets | Set costs against staff and track actual costs against budgets.
8 | Solver | If required a solver can be used to find the best project plan by changing the assigned to.

## ProjectSummary
Project Summary: New expenditure and commissions system. |  |  | Select Month & Year: |  | March | 2025 |  |  |  |  | *Re-Apply Filters (Data) |  |  | March 2025 - (Selected Month!)
TRUE
Remaining
Ref | Project Reference | . | Effort | Start | End | Days | Effort | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Status
STORY 1.1.0 | Gathering Requirements |  | 24 | 2025-01-06 | 2025-01-30 | -35 | 0.48 | 100% | 100% | 100% | 95% | 95% | 98%
STORY 1.2.0 | Define Requirements |  | 32 | 2025-01-31 | 2025-02-19 | -21 | 6.72 | 95% | 100% | 95% | 95% | 10% | 79%
STORY 1.3.0 | System Architecture Design |  | 22 | 2025-02-11 | 2025-03-07 | -9 | 16.72 | 50% | 20% | 20% | 20% | 10% | 24%
STORY 2.1.0 | Design and Plan GUI Development |  | 45 | 2025-03-10 | 2025-03-21 | 3 | 44.1 | 10% | 0% | 0% | 0% | 0% | 2%
STORY 2.2.0 | Design and Plan Server-Side Development |  | 50 | 2025-03-24 | 2025-04-04 | 13 | 50 | 0% | 0% | 0% | 0% | 0% | 0%
STORY 2.3.0 | Plan GUI and Server-Side Testing |  | 25 | 2025-04-07 | 2025-04-11 | 18 | 25 | 0% | 0% | 0% | 0% | 0% | 0%
STORY 3.1.0 | Development Plan |  | 5 | 2025-04-14 | 2025-04-14 | 19 | 5 | 0% | 0% | 0% | 0% | 0% | 0%
STORY 4.1.0 | Phase 1 Development |  | 35 | 2025-04-14 | 2025-04-30 | 31 | 35 | 0% | 0% | 0% | 0% | N/A | 0%
STORY 4.2.0 | Phase 2 Deployment - UAT |  | 17 | 2025-04-15 | 2025-04-23 | 26 | 17 | 0% | 0% | 0% | 0% | 0% | 0%
STORY 4.3.0 | Phase 3 Deployment - PROD |  | 8 | 2025-04-22 | 2025-04-24 | 27 | 8 | 0% | 0% | 0% | 0% | 0% | 0%
STORY 5.1.0 | Finalise Plan for Production |  | 20 | 2025-04-22 | 2025-05-08 | 37 | 20 | 0% | 0% | 0% | 0% | N/A | 0%
STORY 6.1.0 | None |  | 0 |  |  | 0 | 0 | N/A | N/A | N/A | N/A | N/A
STORY 6.2.0 | None |  | 0 |  |  | 0 | 0 | N/A | N/A | N/A | N/A | N/A
| Overall Progress | [11 empty] | 18.45%
| Project Budget |  |  | Estimated | Actual | Tasks Completed - (Done >90%)
| Total |  |  | 7508.5 | 7578.5 | 1594 | 1636 | 42 | 2.635%
| By Department |  |  | Estimated | Actual | Estimated | Actual | Variance | %
| Architect |  |  | 660 | 720 | 0 | 0 | 0 | 0%
| Business Analyst |  |  | 1231 | 1100 | 847 | 716 | -131 | -15.47%
| Database Developer |  |  | 825 | 875 | 125 | 175 | 50 | 40%
| DevOps Engineer |  |  | 200 | 200 | 0 | 0 | 0 | 0%
| Frontend Developer |  |  | 135 | 135 | 0 | 0 | 0 | 0%
| Infrastructure Team |  |  | 0 | 0 | 0 | 0 | 0 | 0%
| IT Support/Helpdesk |  |  | 75 | 75 | 0 | 0 | 0 | 0%
| Performance Lead |  |  | 480 | 480 | 0 | 0 | 0 | 0%
| Product Owner |  |  | 1504 | 1568 | 352 | 448 | 96 | 27.27%
| Server Developer |  |  | 1545 | 1572 | 270 | 297 | 27 | 10%
| Technical Lead |  |  | 160 | 160 | 0 | 0 | 0 | 0%
| Tester |  |  | 417.5 | 417.5 | 0 | 0 | 0 | 0%
| Un-Assigned Role |  |  | 50 | 50 | 0 | 0 | 0 | 0%
| UX Designer |  |  | 226 | 226 | 0 | 0 | 0 | 0%
| 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0%
Formulas:
Days = IF(tbl_project_summary[[#This Row],[End]]<>"",NETWORKDAYS(TODAY(),tbl_project_summary[[#This Row],[End]]),0)

## Report
Completed Tasks (90% or more) Report: New expenditure and commissions system. | [14 empty] | Check Holidays |  | How many days prior to start date to check: | 20 | 0
[15 empty] | Select Ref | Assigned To | Task Start | Task End
Task | Done | Ref | Assigned To | Role | Start Date | End Date | Act | Est | Diff | Elapse | Hols | Est £ | Act £ | Var % | 1.1.1 | Clara Bennett | 2025-01-06 | 2025-01-10
Analyse and Document Competitor Platforms | 100% | 1.1.1 | Clara Bennett | Product Owner | 2025-01-06 | 2025-01-10 | 5 | 5 | 0 | 5 | 0 | 160 | 160 | 0% | Date | Reason | Notes
Gather Requirements and Define User Stories | 100% | 1.1.2 | James Whitmore | Business Analyst | 2025-01-13 | 2025-01-17 | 5 | 6 | -1 | 5 | 0 | 192 | 160 | -16.67% | 2024-12-18 | External Issue | Offsite meeting with client
Plan of Action: Summarise Findings, High Level Objectives and Goals | 100% | 1.1.3 | James Whitmore | Business Analyst | 2025-01-20 | 2025-01-24 | 5 | 5 | 0 | 5 | 0 | 160 | 160 | 0% | 2024-12-25 | Christmas Day | #N/A
Agree Stakeholder Expectations after Initial Review | 95% | 1.1.4 | Clara Bennett | Product Owner | 2025-01-20 | 2025-01-24 | 5 | 3 | 2 | 5 | 0 | 96 | 160 | 66.67% | 2024-12-26 | Boxing Day | #N/A
Define Objectives and Key Performance Indicators (KPIs,etc.) | 95% | 1.1.5 | Liam O'Connor | Business Analyst | 2025-01-27 | 2025-01-30 | 4 | 5 | -1 | 4 | 0 | 175 | 140 | -20% | 2025-01-01 | New Year’s Day | #N/A
Identify New Functionality and Enhancements | 95% | 1.2.1 | James Whitmore | Business Analyst | 2025-01-31 | 2025-02-11 | 8 | 10 | -2 | 12 | 0 | 320 | 256 | -20%
Identify and Document Non-Functional Requirements | 100% | 1.2.2 | Adam Kowalski | Server Developer | 2025-01-27 | 2025-02-19 | 11 | 10 | 1 | 24 | 7 | 270 | 297 | 10%
User Stories to Functional Mapping and Enhancements | 95% | 1.2.3 | Priya Sharma | Database Developer | 2025-01-31 | 2025-02-10 | 7 | 5 | 2 | 11 | 0 | 125 | 175 | 40%
Prioritise Stories and Requirements with Stakeholders | 95% | 1.2.4 | Clara Bennett | Product Owner | 2025-02-11 | 2025-02-14 | 4 | 3 | 1 | 4 | 0 | 96 | 128 | 33.33%
Formulas:
Task Start = XLOOKUP([Select Ref],D:D,G:H,"None")

## ProjectSchedule
Enter Company Name in cell B2.
| New expenditure and commissions system. | Project Start: |  | 2025-01-06 |  |  | Project End: |  |  | 2025-05-08
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 4 | 4 |  |  | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-01-27 to 2025-03-23
REF | TASK | ASSIGNED TO | PROGRESS | START | END | START Wk | Elapsed DAYS | time axis 2025-01-27 to 2025-03-23
Go | Gathering Requirements
1.1.1 | Analyse and Document Competitor Platforms | Clara Bennett-PROD | 100% | 2025-01-06 | 2025-01-10 | 1 | 5
1.1.2 | Gather Requirements and Define User Stories | James Whitmore-BANA | 100% | 2025-01-13 | 2025-01-17 | 2 | 5
1.1.3 | Plan of Action: Summarise Findings, High Level Objectives and Goals | James Whitmore-BANA | 100% | 2025-01-20 | 2025-01-24 | 3 | 5
1.1.4 | Agree Stakeholder Expectations after Initial Review | Clara Bennett-PROD | 95% | 2025-01-20 | 2025-01-24 | 3 | 5
1.1.5 | Define Objectives and Key Performance Indicators (KPIs,etc.) | Liam O'Connor-BANA | 95% | 2025-01-27 | 2025-01-30 | 4 | 4
Go | Define Requirements
1.2.1 | Identify New Functionality and Enhancements | James Whitmore-BANA | 95% | 2025-01-31 | 2025-02-11 | 4 | 12
1.2.2 | Identify and Document Non-Functional Requirements | Adam Kowalski-SERD | 100% | 2025-01-27 | 2025-02-19 | 4 | 24
1.2.3 | User Stories to Functional Mapping and Enhancements | Priya Sharma-DBDE | 95% | 2025-01-31 | 2025-02-10 | 4 | 11
1.2.4 | Prioritise Stories and Requirements with Stakeholders | Clara Bennett-PROD | 95% | 2025-02-11 | 2025-02-14 | 6 | 4
1.2.5 | Publish Documents to Internal Stakeholders and Update | James Whitmore-BANA | 10% | 2025-02-17 | 2025-02-18 | 7 | 2
Go | System Architecture Design
1.3.1 | Document and Agree Key Performance Indicators | Liam Gardner-PERL | 50% | 2025-02-11 | 2025-02-17 | 6 | 7
1.3.2 | Create Workflow Diagrams and a Product Plan | Clara Bennett-PROD | 20% | 2025-02-17 | 2025-02-20 | 7 | 4
1.3.3 | Develop High-Level Technical Specifications | Evelyn Hart-ARCH | 20% | 2025-02-19 | 2025-02-27 | 7 | 9
1.3.4 | Review and Agree Designs with Lead Stakeholders | Clara Bennett-PROD | 20% | 2025-02-28 | 2025-03-06 | 8 | 7
1.3.5 | Start GUI and Server Component Development, and API Implementation | Evelyn Hart-ARCH | 10% | 2025-03-07 | 2025-03-07 | 9 | 1
Go | Design and Plan GUI Development
2.1.1 | Create Wireframes and Mockups. Identify Default Values Required for Trading. | Chloe Martin-UXDE | 10% | 2025-03-10 | 2025-03-21 | 10 | 12
2.1.2 | Identify User Data Flow for Optimal User Experience | James Whitmore-BANA | 0% | 2025-03-10 | 2025-03-21 | 10 | 12
2.1.3 | Develop a Test Plan: Usability, Configuration, etc. | Ryan Carter-TEST | 0% | 2025-03-10 | 2025-03-21 | 10 | 12
2.1.4 | Create a Roadmap and Agree on the Plan | Clara Bennett-PROD | 0% | 2025-03-10 | 2025-03-21 | 10 | 12
2.1.5 | IT Systems and Support - Access | Teddy Smith-ITS | 0% | 2025-03-10 | 2025-03-14 | 10 | 5
Go | Design and Plan Server-Side Development
2.2.1 | Design and Set Up the Database | Priya Sharma-DBDE | 0% | 2025-03-24 | 2025-04-04 | 12 | 12
2.2.2 | Develop Endpoints for the API | Max Patel-SERD | 0% | 2025-03-24 | 2025-04-04 | 12 | 12
2.2.3 | Develop Core Business Logic Services for the App | Adam Kowalski-SERD | 0% | 2025-03-24 | 2025-04-04 | 12 | 12
2.2.4 | Integrate with Market Data (Internal, External, etc.) | Evelyn Hart-ARCH | 0% | 2025-03-24 | 2025-04-04 | 12 | 12
2.2.5 | Document server dataflows and publish | Clara Bennett-PROD | 0% | 2025-03-24 | 2025-04-04 | 12 | 12
Go | Plan GUI and Server-Side Testing
2.3.1 | Plan and Document Tests for the Backend Server | Adam Kowalski-SERD | 0% | 2025-04-07 | 2025-04-11 | 14 | 5
2.3.2 | Document Unit Tests for Electronic Messaging | Hannah Fletcher-TECL | 0% | 2025-04-07 | 2025-04-11 | 14 | 5
2.3.3 | Document Unit Tests for the Frontend | Evelyn Hart-ARCH | 0% | 2025-04-07 | 2025-04-11 | 14 | 5
2.3.4 | Document Tests for All Data Requirements | Priya Sharma-DBDE | 0% | 2025-04-07 | 2025-04-11 | 14 | 5
2.3.5 | Document Performance and Usability Metrics | Liam Gardner-PERL | 0% | 2025-04-07 | 2025-04-11 | 14 | 5
Go | Development Plan
3.1.1 | Develop/Update the Test Plan | Hannah Fletcher-TECL | 0% | 2025-04-14 | 2025-04-14 | 15 | 1
3.1.2 | Execute Tests | Alex Parker-TEST | 0% | 2025-04-14 | 2025-04-14 | 15 | 1
3.1.3 | Log Bugs and Update Documents | Hannah Fletcher-TECL | 0% | 2025-04-14 | 2025-04-14 | 15 | 1
3.1.4 | Conduct System Reliability and Performance Testing | Liam Gardner-PERL | 0% | 2025-04-14 | 2025-04-14 | 15 | 1
3.1.5 | Obtain Product Management and Senior Stakeholder Sign-Off | Clara Bennett-PROD | 0% | 2025-04-14 | 2025-04-14 | 15 | 1
Go | Phase 1 Development
4.1.1 | Server Components | Max Patel-SERD | 0% | 2025-04-14 | 2025-04-29 | 15 | 16
4.1.2 | Frontend | Olivia Brooks-FROD | 0% | 2025-04-14 | 2025-04-22 | 15 | 9
4.1.3 | Database | Priya Sharma-DBDE | 0% | 2025-04-14 | 2025-04-29 | 15 | 16
4.1.4 | Testing | Ryan Carter-TEST | 0% | 2025-04-15 | 2025-04-30 | 15 | 16
|  |  | N/A |  |  |  | 0
Go | Phase 2 Deployment - UAT
4.2.1 | Full UAT deployment | Connor Reed-DEVO | 0% | 2025-04-15 | 2025-04-23 | 15 | 9
4.2.2 | UAT Sever | Max Patel-SERD | 0% | 2025-04-15 | 2025-04-17 | 15 | 3
4.2.3 | UAT Frontend | Hannah Fletcher-TECL | 0% | 2025-04-15 | 2025-04-17 | 15 | 3
4.2.4 | UAT Data | Priya Sharma-DBDE | 0% | 2025-04-15 | 2025-04-17 | 15 | 3
4.2.5 | UAT Performance | Liam Gardner-PERL | 0% | 2025-04-15 | 2025-04-17 | 15 | 3
Go | Phase 3 Deployment - PROD
4.3.1 | Full PRE-PROD deployment | Connor Reed-DEVO | 0% | 2025-04-22 | 2025-04-24 | 16 | 3
4.3.2 | PRE-PROD Sever | Max Patel-SERD | 0% | 2025-04-22 | 2025-04-22 | 16 | 1
4.3.3 | PRE-PROD Frontend | Hannah Fletcher-TECL | 0% | 2025-04-22 | 2025-04-22 | 16 | 1
4.3.4 | PRE-PROD Data | Evelyn Hart-ARCH | 0% | 2025-04-22 | 2025-04-22 | 16 | 1
4.3.5 | PRE-PROD Performance and Monitoring | Liam Gardner-PERL | 0% | 2025-04-22 | 2025-04-23 | 16 | 2
Go | Finalise Plan for Production
5.1.1 | Create a Stakeholder Report and Agree on a Go-Live Date | Un-Assigned-UNAS | 0% | 2025-04-22 | 2025-04-28 | 16 | 7
5.1.2 | Verify Environment Readiness for Go-Live | Max Patel-SERD | 0% | 2025-04-24 | 2025-04-30 | 16 | 7
5.1.3 | Hand Over Production to Support | Hannah Fletcher-TECL | 0% | 2025-04-24 | 2025-04-30 | 16 | 7
5.1.4 | Conduct Post-Production Review and Project Retrospectives | Clara Bennett-PROD | 0% | 2025-05-01 | 2025-05-08 | 17 | 8
|  |  | N/A |  |  |  | 0
Go | None
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
Go | None
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0
|  |  | N/A |  |  |  | 0

## ProjectPlan
| New expenditure and commissions system. | Start Date: | 2025-01-06 |  | Effort |  |  | End Date: | 2025-05-08 | Budget : | 7508.5 | [5 empty] | PCT | Status
Ref | Project | Type | Start Date | End Date | Actual | Est | Done% | Dependency | Notes/Doc Ref/Links | Assigned To | Role | Elapse | Holiday | Day |  |  | N/A | Not Applicable
1.1.0 | Gathering Requirements | StartDate | 2025-01-06 | 45663 | [9 empty] | 1900-01-01 |  |  | 0% | Not Started/Issue
1.1.1 | Analyse and Document Competitor Platforms | Task 1 | 2025-01-06 | 2025-01-10 | 5 | 5 | 100% | 1.1.0 |  | Clara Bennett | Product Owner | 5 | 0 | 1900-01-05 | RoleRef_8 | FALSE | 10% | Initiated
1.1.2 | Gather Requirements and Define User Stories | Task 2 | 2025-01-13 | 2025-01-17 | 5 | 6 | 100% | 1.1.1 | prj_automate_reconciliation.doc | James Whitmore | Business Analyst | 5 | 0 | 1900-01-05 | RoleRef_3 | FALSE | 20% | Plan Created
1.1.3 | Plan of Action: Summarise Findings, High Level Objectives and Goals | Task 3 | 2025-01-20 | 2025-01-24 | 5 | 5 | 100% | 1.1.2 |  | James Whitmore | Business Analyst | 5 | 0 | 1900-01-05 | RoleRef_3 | FALSE | 25% | Work Started
1.1.4 | Agree Stakeholder Expectations after Initial Review | Task 4 | 2025-01-20 | 2025-01-24 | 5 | 3 | 95% | 1.1.2 |  | Clara Bennett | Product Owner | 5 | 0 | 1900-01-05 | RoleRef_8 | FALSE | 50% | Work in Progress
1.1.5 | Define Objectives and Key Performance Indicators (KPIs,etc.) | Task 5 | 2025-01-27 | 2025-01-30 | 4 | 5 | 95% | 1.1.4 |  | Liam O'Connor | Business Analyst | 4 | 0 | 1900-01-04 | RoleRef_3 | FALSE | 80% | Nearly Completed
|  | EndDate | 2025-01-30 |  | 24 | 24 | [5 empty] | 24 |  | 1900-01-04 |  |  | 90% | Review
1.2.0 | Define Requirements | Start | 2025-01-20 |  |  |  |  | 1.1.0 | [5 empty] | 1900-01-01 |  |  | 95% | Ready to Close
1.2.1 | Identify New Functionality and Enhancements | Task 1 | 2025-01-31 | 2025-02-11 | 8 | 10 | 95% | 1.1.5 |  | James Whitmore | Business Analyst | 12 | 0 | 1900-01-02 | RoleRef_3 | FALSE | 100% | Closed
1.2.2 | Identify and Document Non-Functional Requirements | Task 2 | 2025-01-27 | 2025-02-19 | 11 | 10 | 100% | 1.1.3 |  | Adam Kowalski | Server Developer | 24 | 7 | 1900-01-03 | RoleRef_9 | FALSE |  |  |  |  | RoleRef_9
1.2.3 | User Stories to Functional Mapping and Enhancements | Task 3 | 2025-01-31 | 2025-02-10 | 7 | 5 | 95% | 1.1.5 |  | Priya Sharma | Database Developer | 11 | 0 | 1900-01-01 | RoleRef_4 | FALSE | Check Holidays |  | How many days prior to start date to check: | 21 | 0 | 0 | Server Developer
1.2.4 | Prioritise Stories and Requirements with Stakeholders | Task 4 | 2025-02-11 | 2025-02-14 | 4 | 3 | 95% | 1.2.3 |  | Clara Bennett | Product Owner | 4 | 0 | 1900-01-05 | RoleRef_8 | FALSE | Select Ref | Assigned To | Task Start | Task End |  |  | Staff List
1.2.5 | Publish Documents to Internal Stakeholders and Update | Task 5 | 2025-02-17 | 2025-02-18 | 2 | 2 | 10% | 1.2.4 |  | James Whitmore | Business Analyst | 2 | 0 | 1900-01-02 | RoleRef_3 | FALSE | 1.2.2 | Adam Kowalski | 2025-01-27 | 2025-02-19 |  |  | No Staff Assigned
|  | EndDate | 2025-02-19 |  | 32 | 30 | [5 empty] | 53 |  | 1900-01-03 |  |  | Date | Reason | Notes
1.3.0 | System Architecture Design | Start | 2025-01-20 |  |  |  |  | 1.1.0 | [5 empty] | 1900-01-01 |  |  | 2025-01-29 | Holiday-Planned
1.3.1 | Document and Agree Key Performance Indicators | Task 1 | 2025-02-11 | 2025-02-17 | 5 | 5 | 50% | 1.2.3 |  | Liam Gardner | Performance Lead | 7 | 0 | 1900-01-01 | RoleRef_7 | FALSE | 2025-01-30 | Holiday-Planned
1.3.2 | Create Workflow Diagrams and a Product Plan | Task 2 | 2025-02-17 | 2025-02-20 | 4 | 5 | 20% | 1.2.4 |  | Clara Bennett | Product Owner | 4 | 0 | 1900-01-04 | RoleRef_8 | FALSE | 2025-01-31 | Holiday-Planned
1.3.3 | Develop High-Level Technical Specifications | Task 3 | 2025-02-19 | 2025-02-27 | 7 | 5 | 20% | 1.2.5 |  | Evelyn Hart | Architect | 9 | 0 | 1900-01-04 | RoleRef_2 | FALSE | 2025-02-03 | Holiday-Planned
1.3.4 | Review and Agree Designs with Lead Stakeholders | Task 4 | 2025-02-28 | 2025-03-06 | 5 | 5 | 20% | 1.3.3 |  | Clara Bennett | Product Owner | 7 | 0 | 1900-01-04 | RoleRef_8 | FALSE | 2025-02-04 | Holiday-Planned
1.3.5 | Start GUI and Server Component Development, and API Implementation | Task 5 | 2025-03-07 | 2025-03-07 | 1 | 1 | 10% | 1.3.4 |  | Evelyn Hart | Architect | 1 | 0 | 1900-01-05 | RoleRef_2 | FALSE | 2025-02-05 | Holiday-Planned
|  | EndDate | 2025-03-07 |  | 22 | 21 | [5 empty] | 28 |  | 1900-01-05 |  |  | 2025-02-06 | Holiday-Planned
2.1.0 | Design and Plan GUI Development | Start | 2025-03-10 |  |  |  |  | 1.3.5 | [5 empty] | 1900-01-01 |  |  | 2-No Bank Holidays | #N/A | #N/A
2.1.1 | Create Wireframes and Mockups. Identify Default Values Required for Trading. | Task 1 | 2025-03-10 | 2025-03-21 | 10 | 10 | 10% | 1.3.5 |  | Chloe Martin | UX Designer | 12 | 0 | 1900-01-05 | RoleRef_12 | FALSE
2.1.2 | Identify User Data Flow for Optimal User Experience | Task 2 | 2025-03-10 | 2025-03-21 | 10 | 10 | 0% | 1.3.5 |  | James Whitmore | Business Analyst | 12 | 0 | 1900-01-05 | RoleRef_3 | FALSE
2.1.3 | Develop a Test Plan: Usability, Configuration, etc. | Task 3 | 2025-03-10 | 2025-03-21 | 10 | 10 | 0% | 1.3.5 |  | Ryan Carter | Tester | 12 | 0 | 1900-01-05 | RoleRef_11 | FALSE
2.1.4 | Create a Roadmap and Agree on the Plan | Task 4 | 2025-03-10 | 2025-03-21 | 10 | 10 | 0% | 1.3.5 |  | Clara Bennett | Product Owner | 12 | 0 | 1900-01-05 | RoleRef_8 | FALSE
2.1.5 | IT Systems and Support - Access | Task 5 | 2025-03-10 | 2025-03-14 | 5 | 5 | 0% | 1.3.5 |  | Teddy Smith | IT Support/Helpdesk | 5 | 0 | 1900-01-05 | RoleRef_16 | FALSE
|  | EndDate | 2025-03-21 |  | 45 | 45 | [5 empty] | 53 |  | 1900-01-05
2.2.0 | Design and Plan Server-Side Development | Start | 2025-03-24 |  |  |  |  | 2.1.4 | [5 empty] | 1900-01-01
2.2.1 | Design and Set Up the Database | Task 1 | 2025-03-24 | 2025-04-04 | 10 | 10 | 0% | 2.1.4 |  | Priya Sharma | Database Developer | 12 | 0 | 1900-01-05 | RoleRef_4 | FALSE
2.2.2 | Develop Endpoints for the API | Task 2 | 2025-03-24 | 2025-04-04 | 10 | 10 | 0% | 2.1.4 |  | Max Patel | Server Developer | 12 | 0 | 1900-01-05 | RoleRef_9 | FALSE
2.2.3 | Develop Core Business Logic Services for the App | Task 3 | 2025-03-24 | 2025-04-04 | 10 | 10 | 0% | 2.1.4 |  | Adam Kowalski | Server Developer | 12 | 0 | 1900-01-05 | RoleRef_9 | FALSE
2.2.4 | Integrate with Market Data (Internal, External, etc.) | Task 4 | 2025-03-24 | 2025-04-04 | 10 | 10 | 0% | 2.1.4 |  | Evelyn Hart | Architect | 12 | 0 | 1900-01-05 | RoleRef_2 | FALSE
2.2.5 | Document server dataflows and publish | Task 5 | 2025-03-24 | 2025-04-04 | 10 | 10 | 0% | 2.1.4 |  | Clara Bennett | Product Owner | 12 | 0 | 1900-01-05 | RoleRef_8 | FALSE
|  | EndDate | 2025-04-04 |  | 50 | 50 | [5 empty] | 60 |  | 1900-01-05
2.3.0 | Plan GUI and Server-Side Testing | Start | 2025-04-07 |  |  |  |  | 2.2.5 | [5 empty] | 1900-01-01
2.3.1 | Plan and Document Tests for the Backend Server | Task 1 | 2025-04-07 | 2025-04-11 | 5 | 5 | 0% | 2.2.5 |  | Adam Kowalski | Server Developer | 5 | 0 | 1900-01-05 | RoleRef_9 | FALSE
2.3.2 | Document Unit Tests for Electronic Messaging | Task 2 | 2025-04-07 | 2025-04-11 | 5 | 5 | 0% | 2.2.5 |  | Hannah Fletcher | Technical Lead | 5 | 0 | 1900-01-05 | RoleRef_10 | FALSE
2.3.3 | Document Unit Tests for the Frontend | Task 3 | 2025-04-07 | 2025-04-11 | 5 | 5 | 0% | 2.2.5 |  | Evelyn Hart | Architect | 5 | 0 | 1900-01-05 | RoleRef_2 | FALSE
2.3.4 | Document Tests for All Data Requirements | Task 4 | 2025-04-07 | 2025-04-11 | 5 | 5 | 0% | 2.2.5 |  | Priya Sharma | Database Developer | 5 | 0 | 1900-01-05 | RoleRef_4 | FALSE
2.3.5 | Document Performance and Usability Metrics | Task 5 | 2025-04-07 | 2025-04-11 | 5 | 5 | 0% | 2.2.5 |  | Liam Gardner | Performance Lead | 5 | 0 | 1900-01-05 | RoleRef_7 | FALSE
|  | EndDate | 2025-04-11 |  | 25 | 25 | [5 empty] | 25 |  | 1900-01-05
3.1.0 | Development Plan | Start | 2025-04-14 |  |  |  |  | 2.3.5 | [5 empty] | 1900-01-01
3.1.1 | Develop/Update the Test Plan | Task 1 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0% | 2.3.5 |  | Hannah Fletcher | Technical Lead | 1 | 0 | 1900-01-01 | RoleRef_10 | FALSE
3.1.2 | Execute Tests | Task 2 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0% | 2.3.5 |  | Alex Parker | Tester | 1 | 0 | 1900-01-01 | RoleRef_11 | FALSE
3.1.3 | Log Bugs and Update Documents | Task 3 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0% | 2.3.5 |  | Hannah Fletcher | Technical Lead | 1 | 0 | 1900-01-01 | RoleRef_10 | FALSE
3.1.4 | Conduct System Reliability and Performance Testing | Task 4 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0% | 2.3.5 |  | Liam Gardner | Performance Lead | 1 | 0 | 1900-01-01 | RoleRef_7 | FALSE
3.1.5 | Obtain Product Management and Senior Stakeholder Sign-Off | Task 5 | 2025-04-14 | 2025-04-14 | 1 | 1 | 0% | 2.3.5 |  | Clara Bennett | Product Owner | 1 | 0 | 1900-01-01 | RoleRef_8 | FALSE
|  | EndDate | 2025-04-14 |  | 5 | 5 | [5 empty] | 5 |  | 1900-01-01
4.1.0 | Phase 1 Development | Start | 2025-04-14 |  |  |  |  | 2.3.5 | [5 empty] | 1900-01-01
4.1.1 | Server Components | Task 1 | 2025-04-14 | 2025-04-29 | 10 | 10 | 0% | 2.3.5 |  | Max Patel | Server Developer | 16 | 0 | 1900-01-02 | RoleRef_9 | FALSE
4.1.2 | Frontend | Task 2 | 2025-04-14 | 2025-04-22 | 5 | 5 | 0% | 2.3.5 |  | Olivia Brooks | Frontend Developer | 9 | 0 | 1900-01-02 | RoleRef_6 | FALSE
4.1.3 | Database | Task 3 | 2025-04-14 | 2025-04-29 | 10 | 10 | 0% | 2.3.5 |  | Priya Sharma | Database Developer | 16 | 0 | 1900-01-02 | RoleRef_4 | FALSE
4.1.4 | Testing | Task 4 | 2025-04-15 | 2025-04-30 | 10 | 10 | 0% | 3.1.2 |  | Ryan Carter | Tester | 16 | 0 | 1900-01-03 | RoleRef_11 | FALSE
4.1.5 | Frontend Two | Task 5 | 2025-04-14 | 2025-04-14 | 5 | 5 | N/A | 2.3.5 |  | Sofia Moreno | Frontend Developer | 1 | 0 | 1900-01-01 | RoleRef_6 | FALSE
|  | EndDate | 2025-04-30 |  | 35 | 35 | [5 empty] | 58 |  | 1900-01-03
4.2.0 | Phase 2 Deployment - UAT | Start | 2025-04-15 |  |  |  |  | 4.1.5 | [5 empty] | 1900-01-02
4.2.1 | Full UAT deployment | Task 1 | 2025-04-15 | 2025-04-23 | 5 | 5 | 0% | 4.1.5 |  | Connor Reed | DevOps Engineer | 9 | 0 | 1900-01-03 | RoleRef_5 | FALSE
4.2.2 | UAT Sever | Task 2 | 2025-04-15 | 2025-04-17 | 3 | 3 | 0% | 4.1.5 |  | Max Patel | Server Developer | 3 | 0 | 1900-01-04 | RoleRef_9 | FALSE
4.2.3 | UAT Frontend | Task 3 | 2025-04-15 | 2025-04-17 | 3 | 3 | 0% | 4.1.5 |  | Hannah Fletcher | Technical Lead | 3 | 0 | 1900-01-04 | RoleRef_10 | FALSE
4.2.4 | UAT Data | Task 4 | 2025-04-15 | 2025-04-17 | 3 | 3 | 0% | 4.1.5 |  | Priya Sharma | Database Developer | 3 | 0 | 1900-01-04 | RoleRef_4 | FALSE
4.2.5 | UAT Performance | Task 5 | 2025-04-15 | 2025-04-17 | 3 | 3 | 0% | 4.1.5 |  | Liam Gardner | Performance Lead | 3 | 0 | 1900-01-04 | RoleRef_7 | FALSE
|  | EndDate | 2025-04-23 |  | 17 | 17 | [5 empty] | 21 |  | 1900-01-03
4.3.0 | Phase 3 Deployment - PROD | Start | 2025-04-22 |  |  |  |  | 4.2.5 | [5 empty] | 1900-01-02
4.3.1 | Full PRE-PROD deployment | Task 1 | 2025-04-22 | 2025-04-24 | 3 | 3 | 0% | 4.2.5 |  | Connor Reed | DevOps Engineer | 3 | 0 | 1900-01-04 | RoleRef_5 | FALSE
4.3.2 | PRE-PROD Sever | Task 2 | 2025-04-22 | 2025-04-22 | 1 | 1 | 0% | 4.2.5 |  | Max Patel | Server Developer | 1 | 0 | 1900-01-02 | RoleRef_9 | FALSE
4.3.3 | PRE-PROD Frontend | Task 3 | 2025-04-22 | 2025-04-22 | 1 | 1 | 0% | 4.2.5 |  | Hannah Fletcher | Technical Lead | 1 | 0 | 1900-01-02 | RoleRef_10 | FALSE
4.3.4 | PRE-PROD Data | Task 4 | 2025-04-22 | 2025-04-22 | 1 | 1 | 0% | 4.2.5 |  | Evelyn Hart | Architect | 1 | 0 | 1900-01-02 | RoleRef_2 | FALSE
4.3.5 | PRE-PROD Performance and Monitoring | Task 5 | 2025-04-22 | 2025-04-23 | 2 | 2 | 0% | 4.2.5 |  | Liam Gardner | Performance Lead | 2 | 0 | 1900-01-03 | RoleRef_7 | FALSE
|  | EndDate | 2025-04-24 |  | 8 | 8 | [5 empty] | 8 |  | 1900-01-04
5.1.0 | Finalise Plan for Production | Start | 2025-04-22 |  |  |  |  | 4.2.5 | [5 empty] | 1900-01-02
5.1.1 | Create a Stakeholder Report and Agree on a Go-Live Date | Task 1 | 2025-04-22 | 2025-04-28 | 5 | 5 | 0% | 4.2.5 |  | Un-Assigned | Un-Assigned Role | 7 | 0 | 1900-01-01 | RoleRef_1 | FALSE
5.1.2 | Verify Environment Readiness for Go-Live | Task 2 | 2025-04-24 | 2025-04-30 | 5 | 5 | 0% | 4.3.5 |  | Max Patel | Server Developer | 7 | 0 | 1900-01-03 | RoleRef_9 | FALSE
5.1.3 | Hand Over Production to Support | Task 3 | 2025-04-24 | 2025-04-30 | 5 | 5 | 0% | 4.3.5 |  | Hannah Fletcher | Technical Lead | 7 | 0 | 1900-01-03 | RoleRef_10 | FALSE
5.1.4 | Conduct Post-Production Review and Project Retrospectives | Task 4 | 2025-05-01 | 2025-05-08 | 5 | 5 | 0% | 5.1.3 |  | Clara Bennett | Product Owner | 8 | 0 | 1900-01-04 | RoleRef_8 | FALSE
|  | Task 5 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | EndDate | 2025-05-08 |  | 20 | 20 | [5 empty] | 30 |  | 1900-01-04
6.1.0 | None | Start | 2025-01-20 | [10 empty] | 1900-01-01
|  | Task 1 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 2 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 3 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 4 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 5 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | EndDate | 1900-01-01 |  | 0 | 0 | [5 empty] | 5 |  | 1900-01-01
6.2.0 | None | Start | 2025-01-20 | [10 empty] | 1900-01-01
|  | Task 1 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 2 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 3 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 4 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | Task 5 | 1900-01-01 | 1900-01-01 |  |  | N/A |  |  | Un-Assigned | Un-Assigned Role | 1 | 0 | 1900-01-01 | RoleRef_1 | FALSE
|  | EndDate | 1900-01-01 |  | 0 | 0 | [5 empty] | 5 |  | 1900-01-01
Formulas:
Start Date = [Start Date, row above]
Start Date = MAX(F4:[End Date, row above])
Day = IF(OR(tbl_project_planner[[#This Row],[End Date]]="",tbl_project_planner[[#This Row],[End Date]]="#N/A"),WEEKDAY(tbl_project_planner[[#This Row],[Start Date]],1),WEEKDAY(tbl_project_planner[[#This Row],[End Date]],1))

## Information
Short Code | Project Title |  | Project Start Date
STORY | New expenditure and commissions system. |  | 2025-01-06
Select Role
| DevOps Engineer |  |  |  |  | RoleRef_5
Staff List | Task | Done | Ref | Assigned To | Estimate | Actual | Elapsed | Diff | Check Holidays |  | *Re-select Task Ref | 21 | 1
No Staff Assigned | Full UAT deployment | 0% | 4.2.1 | Connor Reed | 5 | 5 | 9 | 0 | Select Ref | Assigned To | Task Start | Task End
| Full PRE-PROD deployment | 0% | 4.3.1 | Connor Reed | 3 | 3 | 3 | 0 | 1.3.4 | Clara Bennett | 2025-02-28 | 2025-03-06
[9 empty] | Date | Reason | Notes

## Holidays
Bank Holidays |  | Staff Holidays - At least one for each staff member |  |  |  |  | Types | Date Generator |  | (up to 25 rows generated)
Title | Date | Staff | Date | Type | Note | Day | Holiday Type | Parameter | Value | Staff | Date | Type
At Least One Holiday | 2020-01-06 | Un-Assigned | 2020-01-01 | Misc | Do not delete! | 1900-01-03 | Holiday-Planned | Start_Date | 2025-01-30 | Chloe Martin | 2025-01-30 | Issue with Task
New Year’s Day | 2024-01-01 | Evelyn Hart | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | Holiday-Unplanned | End_Date | 2025-02-05 | Chloe Martin | 2025-01-31 | Issue with Task
Good Friday | 2024-03-29 | James Whitmore | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | Issue with Task | Staff | Chloe Martin | Chloe Martin | 2025-02-03 | Issue with Task
Easter Monday | 2024-04-01 | Priya Sharma | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | External Issue | Type | Issue with Task | Chloe Martin | 2025-02-04 | Issue with Task
Early May bank holiday | 2024-05-06 | Connor Reed | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | Resource Issue |  |  | Chloe Martin | 2025-02-05 | Issue with Task
Spring bank holiday | 2024-05-27 | Sofia Moreno | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | Start Date Adjustment
Summer bank holiday | 2024-08-26 | Olivia Brooks | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01 | Misc
Christmas Day | 2024-12-25 | Liam Gardner | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Boxing Day | 2024-12-26 | Clara Bennett | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
New Year’s Day | 2025-01-01 | Max Patel | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Good Friday | 2025-04-18 | Adam Kowalski | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Easter Monday | 2025-04-21 | Hannah Fletcher | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Early May bank holiday | 2025-05-05 | Ryan Carter | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Spring bank holiday | 2025-05-26 | Alex Parker | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Summer bank holiday | 2025-08-25 | Chloe Martin | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Christmas Day | 2025-12-25 | Teddy Smith | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Boxing Day | 2025-12-26 | Liam O'Connor | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
New Year’s Day | 2026-01-01 | Zara Chen | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Good Friday | 2026-04-03 | Jamal Ahmed | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Easter Monday | 2026-04-06 | Sofia Rodriguez | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Early May bank holiday | 2026-05-04 | Kwame Osei | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Spring bank holiday | 2026-05-25 | Johan Moro | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Summer bank holiday | 2026-08-31 | Yuki Tanaka | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Christmas Day | 2026-12-25 | Alejandro Gomez | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
Boxing Day | 2026-12-28 | Fatima Al-Mansour | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
|  | Raj Malhotra | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
|  | Olga Ivanova | 2020-01-06 | Misc | Staff Requires at least one date | 1900-01-01
|  | Clara Bennett | 2024-11-22 | Start Date Adjustment |  | 1900-01-05
|  | Clara Bennett | 2024-12-02 | External Issue | Resolving issue with stakeholder | 1900-01-01
|  | Clara Bennett | 2024-12-03 | External Issue | Resolving issue with stakeholder | 1900-01-02
|  | Clara Bennett | 2024-12-18 | External Issue | Offsite meeting with client | 1900-01-03
|  | Olivia Brooks | 2024-12-19 | Holiday-Planned |  | 1900-01-04
|  | Olivia Brooks | 2024-12-20 | Holiday-Planned |  | 1900-01-05
|  | Olivia Brooks | 2024-12-25 | Holiday-Planned |  | 1900-01-03
|  | James Whitmore | 2024-12-30 | Holiday-Planned |  | 1900-01-01
|  | James Whitmore | 2024-12-31 | Holiday-Planned |  | 1900-01-02
|  | James Whitmore | 2025-01-02 | Holiday-Planned |  | 1900-01-04
|  | Evelyn Hart | 2025-01-06 | Holiday-Planned |  | 1900-01-01
|  | James Whitmore | 2025-01-07 | Holiday-Planned |  | 1900-01-02
|  | Priya Sharma | 2025-01-08 | Holiday-Planned |  | 1900-01-03
|  | Connor Reed | 2025-01-09 | External Issue | Higher priority issue | 1900-01-04
|  | Sofia Moreno | 2025-01-10 | Resource Issue | Higher priority issue | 1900-01-05
|  | Liam Gardner | 2025-01-11 | Resource Issue | Higher priority issue | 1900-01-06
|  | Clara Bennett | 2025-01-13 | External Issue |  | 1900-01-01
|  | Oliver Nguyen | 2025-01-13 | Holiday-Planned |  | 1900-01-01
|  | Max Patel | 2025-01-14 | Holiday-Planned |  | 1900-01-02
|  | Hannah Fletcher | 2025-01-15 | Holiday-Planned |  | 1900-01-03
|  | Ryan Carter | 2025-01-16 | Holiday-Planned |  | 1900-01-04
|  | Maya Chen | 2025-01-17 | Holiday-Planned |  | 1900-01-05
|  | Amelia Thompson | 2025-01-18 | Holiday-Planned |  | 1900-01-06
|  | Adam Kowalski | 2025-01-29 | Holiday-Planned |  | 1900-01-03
|  | Adam Kowalski | 2025-01-30 | Holiday-Planned |  | 1900-01-04
|  | Adam Kowalski | 2025-01-31 | Holiday-Planned |  | 1900-01-05
|  | Adam Kowalski | 2025-02-03 | Holiday-Planned |  | 1900-01-01
|  | Adam Kowalski | 2025-02-04 | Holiday-Planned |  | 1900-01-02
|  | Adam Kowalski | 2025-02-05 | Holiday-Planned |  | 1900-01-03
|  | Adam Kowalski | 2025-02-06 | Holiday-Planned |  | 1900-01-04
Formulas:
Day = WEEKDAY(tbl_staff_holidays[[#This Row],[Date]],1)
Date = IFERROR(INDEX(_xlws.FILTER(SEQUENCE([Value, row below]-[Value]+1, , [Value]), WEEKDAY(SEQUENCE([Value, row below]-[Value]+1, , [Value]), 2) < 6), SEQUENCE(25), 1), "")

## Staff
Staff List |  |  |  | Staff Roles
Name | Daily_Rate | Role | RoleRef | Roles | Short Code | ColRef
Un-Assigned | 10 | Un-Assigned Role | RoleRef_1 | Un-Assigned Role | UNAS | RoleRef_1
Hannah Fletcher | 10 | Technical Lead | RoleRef_10 | Architect | ARCH | RoleRef_2
Ryan Carter | 20 | Tester | RoleRef_11 | Business Analyst | BANA | RoleRef_3
Alex Parker | 17.5 | Tester | RoleRef_11 | Database Developer | DBDE | RoleRef_4
Chloe Martin | 22.6 | UX Designer | RoleRef_12 | DevOps Engineer | DEVO | RoleRef_5
Evelyn Hart | 30 | Architect | RoleRef_2 | Frontend Developer | FROD | RoleRef_6
James Whitmore | 32 | Business Analyst | RoleRef_3 | Performance Lead | PERL | RoleRef_7
Priya Sharma | 25 | Database Developer | RoleRef_4 | Product Owner | PROD | RoleRef_8
Connor Reed | 25 | DevOps Engineer | RoleRef_5 | Server Developer | SERD | RoleRef_9
Sofia Moreno | 25 | Frontend Developer | RoleRef_6 | Technical Lead | TECL | RoleRef_10
Olivia Brooks | 27 | Frontend Developer | RoleRef_6 | Tester | TEST | RoleRef_11
Liam Gardner | 30 | Performance Lead | RoleRef_7 | UX Designer | UXDE | RoleRef_12
Clara Bennett | 32 | Product Owner | RoleRef_8 | Infrastructure Team | INTE | RoleRef_13
Max Patel | 30 | Server Developer | RoleRef_9 | Finance | FIN | RoleRef_14
Adam Kowalski | 27 | Server Developer | RoleRef_9 | Operations | OPS | RoleRef_15
Teddy Smith | 15 | IT Support/Helpdesk | RoleRef_16 | IT Support/Helpdesk | ITS | RoleRef_16
Aisha Patel | 40 | Architect | RoleRef_2 | Sales | SAL | RoleRef_17
Liam O'Connor | 35 | Business Analyst | RoleRef_3 | Marketing | MAR | RoleRef_18
Zara Chen | 32 | Database Developer | RoleRef_4 | Account Management | ACCM | RoleRef_19
Jamal Ahmed | 34 | DevOps Engineer | RoleRef_5 | People Operations | HR | RoleRef_20
Sofia Rodriguez | 32 | Frontend Developer | RoleRef_6
Kwame Osei | 36 | Performance Lead | RoleRef_7
Johan Newman | 38 | Product Owner | RoleRef_8
Yuki Tanaka | 35 | Server Developer | RoleRef_9
Alejandro Gomez | 40 | Technical Lead | RoleRef_10
Fatima Al-Mansour | 28 | Tester | RoleRef_11
Raj Malhotra | 310 | UX Designer | RoleRef_12
Olga Ivanova | 33 | Infrastructure Team | RoleRef_13
#N/A
Note on G1: (Use all 20 roles for better performance)

## Data (hidden)
Project Helper Table
ref | Project Reference | Start | End | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Selected | a | b | c | d | e | f | g | h | Status | Story | Effort | Used | check
3 | Gathering Requirements | 2025-01-06 | 2025-01-30 | 100% | 100% | 100% | 95% | 95% | 0 | 4 | 9 | 4 | 5 | 6 | 7 | 8 | 9 | 98% | STORY 1.1.0 | 24 | 0 | Gathering Requirements
10 | Define Requirements | 2025-01-31 | 2025-02-19 | 95% | 100% | 95% | 95% | 10% | 0 | 11 | 16 | 11 | 12 | 13 | 14 | 15 | 16 | 79% | STORY 1.2.0 | 32 | 0 | Define Requirements
17 | System Architecture Design | 2025-02-11 | 2025-03-07 | 50% | 20% | 20% | 20% | 10% | 1 | 18 | 23 | 18 | 19 | 20 | 21 | 22 | 23 | 24% | STORY 1.3.0 | 22 | 0 | System Architecture Design
24 | Design and Plan GUI Development | 2025-03-10 | 2025-03-21 | 10% | 0% | 0% | 0% | 0% | 1 | 25 | 30 | 25 | 26 | 27 | 28 | 29 | 30 | 2% | STORY 2.1.0 | 45 | 0 | Design and Plan GUI Development
31 | Design and Plan Server-Side Development | 2025-03-24 | 2025-04-04 | 0% | 0% | 0% | 0% | 0% | 0 | 32 | 37 | 32 | 33 | 34 | 35 | 36 | 37 | 0% | STORY 2.2.0 | 50 | 0 | Design and Plan Server-Side Development
38 | Plan GUI and Server-Side Testing | 2025-04-07 | 2025-04-11 | 0% | 0% | 0% | 0% | 0% | 0 | 39 | 44 | 39 | 40 | 41 | 42 | 43 | 44 | 0% | STORY 2.3.0 | 25 | 0 | Plan GUI and Server-Side Testing
45 | Development Plan | 2025-04-14 | 2025-04-14 | 0% | 0% | 0% | 0% | 0% | 0 | 46 | 51 | 46 | 47 | 48 | 49 | 50 | 51 | 0% | STORY 3.1.0 | 5 | 0 | Development Plan
52 | Phase 1 Development | 2025-04-14 | 2025-04-30 | 0% | 0% | 0% | 0% | N/A | 0 | 53 | 58 | 53 | 54 | 55 | 56 | 57 | 58 | 0% | STORY 4.1.0 | 35 | 1 | Phase 1 Development
59 | Phase 2 Deployment - UAT | 2025-04-15 | 2025-04-23 | 0% | 0% | 0% | 0% | 0% | 0 | 60 | 65 | 60 | 61 | 62 | 63 | 64 | 65 | 0% | STORY 4.2.0 | 17 | 0 | Phase 2 Deployment - UAT
66 | Phase 3 Deployment - PROD | 2025-04-22 | 2025-04-24 | 0% | 0% | 0% | 0% | 0% | 0 | 67 | 72 | 67 | 68 | 69 | 70 | 71 | 72 | 0% | STORY 4.3.0 | 8 | 0 | Phase 3 Deployment - PROD
73 | Finalise Plan for Production | 2025-04-22 | 2025-05-08 | 0% | 0% | 0% | 0% | N/A | 0 | 74 | 79 | 74 | 75 | 76 | 77 | 78 | 79 | 0% | STORY 5.1.0 | 20 | 1 | Finalise Plan for Production
80 | None |  |  | N/A | N/A | N/A | N/A | N/A | 0 | 81 | 86 | 81 | 82 | 83 | 84 | 85 | 86 | -1% | STORY 6.1.0 | 0 | 5 | None
87 | None |  |  | N/A | N/A | N/A | N/A | N/A | 0 | 88 | 93 | 88 | 89 | 90 | 91 | 92 | 93 | -1% | STORY 6.2.0 | 0 | 5 | None
| Available In Project | Years |  | ProjectMonths
| March | 2025 |  | January
February
March
|  |  |  | April | Start
|  |  |  | May | End
| Selected Month and Year | March | 2025 |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | [6 empty] | Weeks Used |  | SEQ
[5 empty] | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | [6 empty] | 1 |  | 1
PCT | Status | Month | All |  | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | [6 empty] | 4 |  | 2
N/A | Not Applicable | 0 | 12 |  | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | [6 empty] | 7 |  | 3
0% | Not Started/Issue | 4 | 37 |  | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | [6 empty] | 10 |  | 4
10% | Initiated | 2 | 3 |  | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | [6 empty] | 13 |  | 0
20% | Plan Created | 3 | 3 |  | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | [6 empty] | 16 |  | 6
25% | Work Started | 0 | 0 | Project Reference: | [15 empty] | 7
50% | Work in Progress | 1 | 1 | PCT% | Done | To Do | [13 empty] | 8
80% | Nearly Completed | 0 | 0 |  | 13% | 87% | [13 empty] | 9
90% | Review | 0 | 0 | [16 empty] | 10
95% | Ready to Close | 0 | 5 | FALSE | [15 empty] | 12
100% | Closed | 0 | 4 | [16 empty] | 14
15
Line Chart Data
Date | Project | Height | Axis | [16 empty] | 16
2025-01-30 | STORY 1.1.0 | 1 | 0 | 2025-01-30 | [15 empty] | 17
2025-02-19 | STORY 1.2.0 | -1 | 0
2025-03-07 | STORY 1.3.0 | 1 | 0
2025-03-21 | STORY 2.1.0 | -1 | 0 |  | Dynamic Label: |  |  | March 2025 Overall Progress
2025-04-04 | STORY 2.2.0 | 1 | 0
2025-04-11 | STORY 2.3.0 | -1 | 0
2025-04-14 | STORY 3.1.0 | 1 | 0
2025-04-30 | STORY 4.1.0 | -1 | 0
2025-04-23 | STORY 4.2.0 | 1 | 0
2025-04-24 | STORY 4.3.0 | -1 | 0
2025-05-08 | STORY 5.1.0 | 1 | 0 | [20 empty] | =FILTER(CHOOSE({1,2,3,4}, tbl_AssignRole[Ref], tbl_AssignRole[Desc], tbl_AssignRole[Used],tbl_AssignRole[Assigned]), tbl_AssignRole[Role] = C34, "No match")
#N/A | #N/A | #N/A | #N/A | [20 empty] | =INDIRECT(X56,TRUE)
#N/A | #N/A | #N/A | #N/A | [20 empty] | =IFERROR(TOCOL(FILTER(tbl_staff_list[Name],tbl_staff_list[RoleRef]=D55,),1),"No Staff Assigned")
Drop Down For Project
Selected | RoleRef_1 | RoleRef_2 | RoleRef_3 | RoleRef_4 | RoleRef_5 | RoleRef_6 | RoleRef_7 | RoleRef_8 | RoleRef_9 | RoleRef_10 | RoleRef_11 | RoleRef_12 | RoleRef_13 | RoleRef_14 | RoleRef_15 | RoleRef_16 | RoleRef_17 | RoleRef_18 | RoleRef_19 | RoleRef_20 |  | Used_Roles | Architect | No Staff Assigned | TRUE | Used_done | Info_task_ref
| No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned | No Staff Assigned |  | Un-Assigned Role | RoleRef_2 |  | TRUE | 1.1.1 | 4.2.1
[22 empty] | Technical Lead | RoleRef_2 |  |  | 1.1.2 | 4.3.1
[22 empty] | Tester |  |  |  | 1.1.3
[22 empty] | UX Designer |  |  |  | 1.1.4
[22 empty] | Architect |  |  |  | 1.1.5
[22 empty] | Business Analyst |  |  |  | 1.2.1
[22 empty] | Database Developer |  |  |  | 1.2.2
[22 empty] | DevOps Engineer |  |  |  | 1.2.3
[22 empty] | Frontend Developer |  |  |  | 1.2.4
Performance Lead
Product Owner
Server Developer
[22 empty] | IT Support/Helpdesk |  |  | 4.2.1
[22 empty] | Infrastructure Team |  |  | 4.3.1
0
Chk | Ref | Desc | Done | Assigned | Role | ShortCode | AssigRole | Actual | Est | Start_date | End_Date | Elapse | Hols | Rate | A_Cost | E_Cost |  |  | Used_ref | 1.1.1
1.1.1 | 1.1.1 | Analyse and Document Competitor Platforms | 100% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 5 | 5 | 2025-01-06 | 2025-01-10 | 5 | 0 | 32 | 160 | 160 |  |  | 1.1.1 | 1.1.2 |  | =IFERROR(IF(AB55=FILTER(tbl_staff_list[Name],tbl_staff_list[Role]=Y55,),FALSE,TRUE),"No Staff Assigned")
1.1.2 | 1.1.2 | Gather Requirements and Define User Stories | 100% | James Whitmore | Business Analyst | BANA | James Whitmore-BANA | 5 | 6 | 2025-01-13 | 2025-01-17 | 5 | 0 | 32 | 160 | 192 |  |  | 1.1.2 | 1.1.3 |  | =IFERROR(IF(STAFF=FILTER(tbl_staff_list[Name],tbl_staff_list[Role]=ROLE,),FALSE,TRUE),"No Staff Assigned")
1.1.3 | 1.1.3 | Plan of Action: Summarise Findings, High Level Objectives and Goals | 100% | James Whitmore | Business Analyst | BANA | James Whitmore-BANA | 5 | 5 | 2025-01-20 | 2025-01-24 | 5 | 0 | 32 | 160 | 160 |  |  | 1.1.3 | 1.1.4
1.1.4 | 1.1.4 | Agree Stakeholder Expectations after Initial Review | 95% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 5 | 3 | 2025-01-20 | 2025-01-24 | 5 | 0 | 32 | 160 | 96 |  |  | 1.1.4 | 1.1.5
1.1.5 | 1.1.5 | Define Objectives and Key Performance Indicators (KPIs,etc.) | 95% | Liam O'Connor | Business Analyst | BANA | Liam O'Connor-BANA | 4 | 5 | 2025-01-27 | 2025-01-30 | 4 | 0 | 35 | 140 | 175 |  |  | 1.1.5 | 1.2.1
1.2.1 | 1.2.1 | Identify New Functionality and Enhancements | 95% | James Whitmore | Business Analyst | BANA | James Whitmore-BANA | 8 | 10 | 2025-01-31 | 2025-02-11 | 12 | 0 | 32 | 256 | 320 |  |  | 1.2.1 | 1.2.2
1.2.2 | 1.2.2 | Identify and Document Non-Functional Requirements | 100% | Adam Kowalski | Server Developer | SERD | Adam Kowalski-SERD | 11 | 10 | 2025-01-27 | 2025-02-19 | 24 | 7 | 27 | 297 | 270 |  |  | 1.2.2 | 1.2.3
1.2.3 | 1.2.3 | User Stories to Functional Mapping and Enhancements | 95% | Priya Sharma | Database Developer | DBDE | Priya Sharma-DBDE | 7 | 5 | 2025-01-31 | 2025-02-10 | 11 | 0 | 25 | 175 | 125 |  |  | 1.2.3 | 1.2.4
1.2.4 | 1.2.4 | Prioritise Stories and Requirements with Stakeholders | 95% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 4 | 3 | 2025-02-11 | 2025-02-14 | 4 | 0 | 32 | 128 | 96 |  |  | 1.2.4 | 1.2.5
1.2.5 | 1.2.5 | Publish Documents to Internal Stakeholders and Update | 10% | James Whitmore | Business Analyst | BANA | James Whitmore-BANA | 2 | 2 | 2025-02-17 | 2025-02-18 | 2 | 0 | 32 | 64 | 64 |  |  | 1.2.5 | 1.3.1
1.3.1 | 1.3.1 | Document and Agree Key Performance Indicators | 50% | Liam Gardner | Performance Lead | PERL | Liam Gardner-PERL | 5 | 5 | 2025-02-11 | 2025-02-17 | 7 | 0 | 30 | 150 | 150 |  |  | 1.3.1 | 1.3.2
1.3.2 | 1.3.2 | Create Workflow Diagrams and a Product Plan | 20% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 4 | 5 | 2025-02-17 | 2025-02-20 | 4 | 0 | 32 | 128 | 160 |  |  | 1.3.2 | 1.3.3
1.3.3 | 1.3.3 | Develop High-Level Technical Specifications | 20% | Evelyn Hart | Architect | ARCH | Evelyn Hart-ARCH | 7 | 5 | 2025-02-19 | 2025-02-27 | 9 | 0 | 30 | 210 | 150 |  |  | 1.3.3 | 1.3.4
1.3.4 | 1.3.4 | Review and Agree Designs with Lead Stakeholders | 20% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 5 | 5 | 2025-02-28 | 2025-03-06 | 7 | 0 | 32 | 160 | 160 |  |  | 1.3.4 | 1.3.5
1.3.5 | 1.3.5 | Start GUI and Server Component Development, and API Implementation | 10% | Evelyn Hart | Architect | ARCH | Evelyn Hart-ARCH | 1 | 1 | 2025-03-07 | 2025-03-07 | 1 | 0 | 30 | 30 | 30 |  |  | 1.3.5 | 2.1.1
2.1.1 | 2.1.1 | Create Wireframes and Mockups. Identify Default Values Required for Trading. | 10% | Chloe Martin | UX Designer | UXDE | Chloe Martin-UXDE | 10 | 10 | 2025-03-10 | 2025-03-21 | 12 | 0 | 22.6 | 226 | 226 |  |  | 2.1.1 | 2.1.2
2.1.2 | 2.1.2 | Identify User Data Flow for Optimal User Experience | 0% | James Whitmore | Business Analyst | BANA | James Whitmore-BANA | 10 | 10 | 2025-03-10 | 2025-03-21 | 12 | 0 | 32 | 320 | 320 |  |  | 2.1.2 | 2.1.3
2.1.3 | 2.1.3 | Develop a Test Plan: Usability, Configuration, etc. | 0% | Ryan Carter | Tester | TEST | Ryan Carter-TEST | 10 | 10 | 2025-03-10 | 2025-03-21 | 12 | 0 | 20 | 200 | 200 |  |  | 2.1.3 | 2.1.4
2.1.4 | 2.1.4 | Create a Roadmap and Agree on the Plan | 0% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 10 | 10 | 2025-03-10 | 2025-03-21 | 12 | 0 | 32 | 320 | 320 |  |  | 2.1.4 | 2.1.5
2.1.5 | 2.1.5 | IT Systems and Support - Access | 0% | Teddy Smith | IT Support/Helpdesk | ITS | Teddy Smith-ITS | 5 | 5 | 2025-03-10 | 2025-03-14 | 5 | 0 | 15 | 75 | 75 |  |  | 2.1.5 | 2.2.1
2.2.1 | 2.2.1 | Design and Set Up the Database | 0% | Priya Sharma | Database Developer | DBDE | Priya Sharma-DBDE | 10 | 10 | 2025-03-24 | 2025-04-04 | 12 | 0 | 25 | 250 | 250 |  |  | 2.2.1 | 2.2.2
2.2.2 | 2.2.2 | Develop Endpoints for the API | 0% | Max Patel | Server Developer | SERD | Max Patel-SERD | 10 | 10 | 2025-03-24 | 2025-04-04 | 12 | 0 | 30 | 300 | 300 |  |  | 2.2.2 | 2.2.3
2.2.3 | 2.2.3 | Develop Core Business Logic Services for the App | 0% | Adam Kowalski | Server Developer | SERD | Adam Kowalski-SERD | 10 | 10 | 2025-03-24 | 2025-04-04 | 12 | 0 | 27 | 270 | 270 |  |  | 2.2.3 | 2.2.4
2.2.4 | 2.2.4 | Integrate with Market Data (Internal, External, etc.) | 0% | Evelyn Hart | Architect | ARCH | Evelyn Hart-ARCH | 10 | 10 | 2025-03-24 | 2025-04-04 | 12 | 0 | 30 | 300 | 300 |  |  | 2.2.4 | 2.2.5
2.2.5 | 2.2.5 | Document server dataflows and publish | 0% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 10 | 10 | 2025-03-24 | 2025-04-04 | 12 | 0 | 32 | 320 | 320 |  |  | 2.2.5 | 2.3.1
2.3.1 | 2.3.1 | Plan and Document Tests for the Backend Server | 0% | Adam Kowalski | Server Developer | SERD | Adam Kowalski-SERD | 5 | 5 | 2025-04-07 | 2025-04-11 | 5 | 0 | 27 | 135 | 135 |  |  | 2.3.1 | 2.3.2
2.3.2 | 2.3.2 | Document Unit Tests for Electronic Messaging | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 5 | 5 | 2025-04-07 | 2025-04-11 | 5 | 0 | 10 | 50 | 50 |  |  | 2.3.2 | 2.3.3
2.3.3 | 2.3.3 | Document Unit Tests for the Frontend | 0% | Evelyn Hart | Architect | ARCH | Evelyn Hart-ARCH | 5 | 5 | 2025-04-07 | 2025-04-11 | 5 | 0 | 30 | 150 | 150 |  |  | 2.3.3 | 2.3.4
2.3.4 | 2.3.4 | Document Tests for All Data Requirements | 0% | Priya Sharma | Database Developer | DBDE | Priya Sharma-DBDE | 5 | 5 | 2025-04-07 | 2025-04-11 | 5 | 0 | 25 | 125 | 125 |  |  | 2.3.4 | 2.3.5
2.3.5 | 2.3.5 | Document Performance and Usability Metrics | 0% | Liam Gardner | Performance Lead | PERL | Liam Gardner-PERL | 5 | 5 | 2025-04-07 | 2025-04-11 | 5 | 0 | 30 | 150 | 150 |  |  | 2.3.5 | 3.1.1
3.1.1 | 3.1.1 | Develop/Update the Test Plan | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 0 | 10 | 10 | 10 |  |  | 3.1.1 | 3.1.2
3.1.2 | 3.1.2 | Execute Tests | 0% | Alex Parker | Tester | TEST | Alex Parker-TEST | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 0 | 17.5 | 17.5 | 17.5 |  |  | 3.1.2 | 3.1.3
3.1.3 | 3.1.3 | Log Bugs and Update Documents | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 0 | 10 | 10 | 10 |  |  | 3.1.3 | 3.1.4
3.1.4 | 3.1.4 | Conduct System Reliability and Performance Testing | 0% | Liam Gardner | Performance Lead | PERL | Liam Gardner-PERL | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 0 | 30 | 30 | 30 |  |  | 3.1.4 | 3.1.5
3.1.5 | 3.1.5 | Obtain Product Management and Senior Stakeholder Sign-Off | 0% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 0 | 32 | 32 | 32 |  |  | 3.1.5 | 4.1.1
4.1.1 | 4.1.1 | Server Components | 0% | Max Patel | Server Developer | SERD | Max Patel-SERD | 10 | 10 | 2025-04-14 | 2025-04-29 | 16 | 0 | 30 | 300 | 300 |  |  | 4.1.1 | 4.1.2
4.1.2 | 4.1.2 | Frontend | 0% | Olivia Brooks | Frontend Developer | FROD | Olivia Brooks-FROD | 5 | 5 | 2025-04-14 | 2025-04-22 | 9 | 0 | 27 | 135 | 135 |  |  | 4.1.2 | 4.1.3
4.1.3 | 4.1.3 | Database | 0% | Priya Sharma | Database Developer | DBDE | Priya Sharma-DBDE | 10 | 10 | 2025-04-14 | 2025-04-29 | 16 | 0 | 25 | 250 | 250 |  |  | 4.1.3 | 4.1.4
4.1.4 | 4.1.4 | Testing | 0% | Ryan Carter | Tester | TEST | Ryan Carter-TEST | 10 | 10 | 2025-04-15 | 2025-04-30 | 16 | 0 | 20 | 200 | 200 |  |  | 4.1.4 | 4.1.5
4.1.5 | 4.1.5 | Frontend Two | N/A |  |  |  | - | 5 | 5 | 2025-04-14 | 2025-04-14 | 1 | 0 | 0 | 0 | 0 |  |  | 4.1.5 | 4.2.1
4.2.1 | 4.2.1 | Full UAT deployment | 0% | Connor Reed | DevOps Engineer | DEVO | Connor Reed-DEVO | 5 | 5 | 2025-04-15 | 2025-04-23 | 9 | 0 | 25 | 125 | 125 |  |  | 4.2.1 | 4.2.2
4.2.2 | 4.2.2 | UAT Sever | 0% | Max Patel | Server Developer | SERD | Max Patel-SERD | 3 | 3 | 2025-04-15 | 2025-04-17 | 3 | 0 | 30 | 90 | 90 |  |  | 4.2.2 | 4.2.3
4.2.3 | 4.2.3 | UAT Frontend | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 3 | 3 | 2025-04-15 | 2025-04-17 | 3 | 0 | 10 | 30 | 30 |  |  | 4.2.3 | 4.2.4
4.2.4 | 4.2.4 | UAT Data | 0% | Priya Sharma | Database Developer | DBDE | Priya Sharma-DBDE | 3 | 3 | 2025-04-15 | 2025-04-17 | 3 | 0 | 25 | 75 | 75 |  |  | 4.2.4 | 4.2.5
4.2.5 | 4.2.5 | UAT Performance | 0% | Liam Gardner | Performance Lead | PERL | Liam Gardner-PERL | 3 | 3 | 2025-04-15 | 2025-04-17 | 3 | 0 | 30 | 90 | 90 |  |  | 4.2.5 | 4.3.1
4.3.1 | 4.3.1 | Full PRE-PROD deployment | 0% | Connor Reed | DevOps Engineer | DEVO | Connor Reed-DEVO | 3 | 3 | 2025-04-22 | 2025-04-24 | 3 | 0 | 25 | 75 | 75 |  |  | 4.3.1 | 4.3.2
4.3.2 | 4.3.2 | PRE-PROD Sever | 0% | Max Patel | Server Developer | SERD | Max Patel-SERD | 1 | 1 | 2025-04-22 | 2025-04-22 | 1 | 0 | 30 | 30 | 30 |  |  | 4.3.2 | 4.3.3
4.3.3 | 4.3.3 | PRE-PROD Frontend | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 1 | 1 | 2025-04-22 | 2025-04-22 | 1 | 0 | 10 | 10 | 10 |  |  | 4.3.3 | 4.3.4
4.3.4 | 4.3.4 | PRE-PROD Data | 0% | Evelyn Hart | Architect | ARCH | Evelyn Hart-ARCH | 1 | 1 | 2025-04-22 | 2025-04-22 | 1 | 0 | 30 | 30 | 30 |  |  | 4.3.4 | 4.3.5
4.3.5 | 4.3.5 | PRE-PROD Performance and Monitoring | 0% | Liam Gardner | Performance Lead | PERL | Liam Gardner-PERL | 2 | 2 | 2025-04-22 | 2025-04-23 | 2 | 0 | 30 | 60 | 60 |  |  | 4.3.5 | 5.1.1
5.1.1 | 5.1.1 | Create a Stakeholder Report and Agree on a Go-Live Date | 0% | Un-Assigned | Un-Assigned Role | UNAS | Un-Assigned-UNAS | 5 | 5 | 2025-04-22 | 2025-04-28 | 7 | 0 | 10 | 50 | 50 |  |  | 5.1.1 | 5.1.2
5.1.2 | 5.1.2 | Verify Environment Readiness for Go-Live | 0% | Max Patel | Server Developer | SERD | Max Patel-SERD | 5 | 5 | 2025-04-24 | 2025-04-30 | 7 | 0 | 30 | 150 | 150 |  |  | 5.1.2 | 5.1.3
5.1.3 | 5.1.3 | Hand Over Production to Support | 0% | Hannah Fletcher | Technical Lead | TECL | Hannah Fletcher-TECL | 5 | 5 | 2025-04-24 | 2025-04-30 | 7 | 0 | 10 | 50 | 50 |  |  | 5.1.3 | 5.1.4
5.1.4 | 5.1.4 | Conduct Post-Production Review and Project Retrospectives | 0% | Clara Bennett | Product Owner | PROD | Clara Bennett-PROD | 5 | 5 | 2025-05-01 | 2025-05-08 | 8 | 0 | 32 | 160 | 160 |  |  | 5.1.4
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
N/A | 0 |  | N/A |  |  |  | - | [6 empty] | 0 | 0 | 0
65 | [14 empty] | 7578.5 | 7508.5
|  | Row Labels | Sum of E_Cost | Sum of A_Cost
|  | Architect | 7700 | 7700
|  | Business Analyst | 13300 | 12600
|  | Database Developer | 9900 | 9900
|  | DevOps Engineer | 2400 | 2400
|  | Frontend Developer | 1750 | 1750
|  | Performance Lead | 6400 | 6400
|  | Product Owner | 23500 | 23500
|  | Server Developer | 23050 | 23050
|  | Technical Lead | 4000 | 4000
|  | Tester | 5200 | 5200
|  | Un-Assigned Role | 250 | 250
|  | UX Designer | 2500 | 2500
|  | Grand Total | 99950 | 99250
Formulas:
Start = IF(tbl_project_helper[[#This Row],[Used]]<5,INDIRECT("ProjectPlan!E"&[a]),"")
End = IF(tbl_project_helper[[#This Row],[Used]]<5,INDIRECT("ProjectPlan!E"&[b]),"")
Task 2 = SEQUENCE(6,7,DATEVALUE([Start, row above]&[End, row above])-WEEKDAY(DATEVALUE([Start, row above]&[End, row above])-1, 2)+0)
a = IFERROR(XLOOKUP([Project Reference],tbl_project_planner[Ref],tbl_project_planner[Start Date],,0,),"")
b = IFERROR(XLOOKUP([Project Reference],tbl_project_planner[Ref],tbl_project_planner[End Date],,0,),"")